MONMOUTH COUNCIL

PHILMONT SCOUT RANCH

YEAR 2000 TRIP PREPARATION PLAN

LISTED BELOW IS THE TENTATIVE SCHEDULE OF THE ACTIVITIES FOR THE YEAR 2000 MONMOUTH COUNCIL  CONTINGENT TRIP TO PHILMONT SCOUT RANCH.

JUL 1998 	- ACTIVITIES COMMITTEE RECRUITS CONTINGENT LEADER

- PHILMONT RESERVATION REQUEST WAS SENT IN FEBRUARY

- PHILMONT RESERVATION FOR YEAR 2000 WAS CONFIRMED IN MARCH 1998

DEC1998	- DETERMINE  DATES FOR NEXT PHILMONT TRIP FOR COUNCIL CALENDAR

JAN 1999	- NOTICE IN SCOUTING TRAIL (MAR-APR ISSUE) FOR ADULT ADVISOR MEETING AND

APPLICATION FORMS AVAILABLE.

FEB 1999	- DIRECT MAILING TO TROOPS AND POSTS

CALL FOR LEADERSHIP TO UNIT LEADERS AND COMMITTEE CHAIRPERSONS

MAR 1999	- INITIAL ADVISOR ORGANIZATIONAL MEETING

- ADVISOR REQUIREMENTS

- COMMITTEE ASSIGNMENTS

- PROMOTIONAL ACTIVITIES

- OPEN HOUSE ARRANGEMENTS

- OTHER MATTERS

- NOTICE IN SCOUTING TRAIL (MAY-JUN) FOR ADULT ADVISORS & SEPARATE NOTICE FOR

SCOUT OPEN HOUSE MEETING IN SEPTEMBER

- MAKE RESERVATION WITH OCEAN TOWNSHIP FOR USE OF RECREATIONAL CENTER ON

WEST PARK AVENUE

- SET MEETING DATES, SHAKEDOWN HIKE DATES, CONSERVATION WEEKEND DATE &

CONTINGENT MEETING DATE

APR 1999	- COMMITTEE MEMBERS TO ATTEND DISTRICT ROUNDTABLES TO PROMOTE YEAR 2000

PHILMONT TRIP

- ADVISOR MEETING

- RESERVE LAWRENCE TRAINING CENTER @ QUAIL HILL SCOUT RESV. FOR 1ST CONTINGENT MEETING

AND OTHER COMMITTEE MEETINGS.

MAY 1999	- RESERVATIONS TO BE MADE WHERE POSSIBLE FOR ALL EVENTS AND ACTIVITIES.

- GENERAL ANNOUNCEMENT OF PHILMONT 2000 TRIP TO ALL SCOUT AND EXPLORER

TROOPS AND ALSO IN MAY SCOUTING TRAIL.

- CALL COLORADO STATE & COLORADO SPRINGS FOR TOURISM BROCHURE

- ADVISOR MEETING

JUN 1999	- ESTIMATED BUDGET TO BE COMPLETED AND SUBMITTED FOR REVIEW.  COST PER SCOUT TO

BE ESTIMATED.

- BEGIN CAMP PROMOTIONS AT FORESTBURG

- PHILMONT ADULT SHAKEDOWN HIKE

- HANDOUT PHILMONT NOTES

- ADVISOR MEETING

- CALL PHILMONT FOR CURRENT YEAR “PEAKS” BOOK, GUIDEBOOK TO ADVENTURE AND MEDICAL FORM.

- MAKE RESERVATION FOR NEXT YEAR FOR KOSHARE INDIAN HOSTEL WITH MEALS INCLUDED.

JUL 1999	- CAMP PROMOTIONS TO CONTINUE FOR ALL SESSIONS AT FORESTBURG

- PREPARE SCOUT MAILING MATERIAL

- PREPARE ARTICLE FOR “SCOUTING TRAIL” (SEP-OCT ISSUE) FOR OPEN HOUSE

- SUBMIT REQUESTS FOR AIRLINE RESERVATIONS FOR FOLLOWING YEAR.

AUG 1999	- CAMP PROMOTIONS TO CONTINUE FOR ALL SESSIONS AT FORESTBURG.

- INFORMATION TO BE SENT TO ALL SCOUTS AND EXPLORERS ANNOUNCING OPEN HOUSE

MEETING IN SEPTEMBER

- ADVISOR MEETING -	REVIEW FINAL ARRANGEMENTS FOR OPEN HOUSE

- REVIEW PLANS FOR 1ST CONTINGENT MEETING AND PROGRESS OF

PLANS FOR SHAKEDOWN HIKE

- FINALIZE COMMITTEE ASSIGNMENTS FOR ALL ACTIVITIES

- REVIEW PRELIMINARY BUDGET BASED ON CURRENT INFORMATION.

- HAVE SCOUT EXECUTIVE CONTACT PHILMONT TO REQUEST AN EXTENSION TO MAKE THE FIRST

PAYMENT.

SEP 1999	- OPEN HOUSE TO BE HELD ON SEPTEMBER 15TH AT OCEAN TOWNSHIP RECREATIONAL

CENTER IN OAKHURST. LIST OF ALL SCHEDULED ACTIVITIES TO BE PROVIDED TO APPLICANTS WHEN INITIAL PAYMENT IS RECEIVED.  INFORMATION TO BE MAILED TO THOSE WHOSE APPLICATIONS ARE RECEIVED IN THE MAIL.

- ALL SCOUT APPLICATIONS TO BE REVIEWED BY COMMITTEE.

- PHILMONT CONTINGENT MEETING TO BE HELD ON SEPTEMBER 29TH TO REVIEW SHAKEDOWN HIKE

INFORMATION AND REQUIREMENTS AND PROVIDE OTHER INFORMATION ON PHILMONT

- FORM TENTATIVE CREWS

- REGISTRATION FEE DUE TO PHILMONT SCOUT RANCH ($50/PERSON)

- NOTICE IN “SCOUTING TRAIL” (FOR ADDITIONAL SCOUTS, IF REQUIRED) (NOV-DEC ISSUE)

- ADVISOR MEETING: - REVIEW APPLICATIONS

- REVIEW TENTATIVE CREWS

- GO OVER PLANS FOR HIKE & 1ST CONTINGENT MEETING

- DISTRIBUTE CREW MEETING PROGRAM AIDS/SUGGESTIONS/TOPICS.

OCT 1999	- FROM APPLICATIONS RECEIVED, FINALIZE CREWS

- FIRST CONTINGENT SHAKEDOWN HIKE SCHEDULED TO BE HELD OCTOBER 8, 9, 10.

LOCATION TO BE DETERMINED.

- EVALUATE SCOUT &  ADULT CAPABILITIES

- ADVISOR MEETING

- SET DATES & ARRANGE FOR INSTRUCTORS FOR CPR/FIRST AID TRAINING.

- REVIEW GUIDEBOOK TO ADVENTURE & “PEAKS” BOOK AT ADVISOR COMMITTEE MEETING.

- COUNCIL EXECUTIVE, PHILMONT ADVISOR, ACTIVITIES CHAIRPERSON & PHILMONT CONTINGENT LEADER

TO MEET TO REVIEW & APPROVE ADULT ADVISORS

NOV 1999	- ADVISOR MEETING

- PHILMONT PAYMENT, FIRST HALF DUE (REMAINDER DUE IN MAY)

- ARTICLE IN “SCOUTING TRAIL” (IF REQUIRED)(JAN-FEB ISSUE)

- CREW MEETINGS

- MAKE PIKE’S PEAK RESERVATIONS

- RETURN WAITE PHILLIPS SCHOLARSHIP INFO TO NE REGION BY NOV 17.

DEC 1999	- RECEIVE & DISTRIBUTE PHILMONT HEALTH & MEDICAL RECORD WITH MEDICAL ADDENDUM.

- MAKE RESERVATION AT COLORADO SPRINGS NATIONAL GUARD ARMORY

JAN 2000	- CREW MEETINGS

- ADVISOR MEETING - GO OVER PEAKS BOOK, ETC.

- PROVIDE SCHOLARSHIP NAMES TO PHILMONT & NE REGION BY JAN 30.

- CHECK ON RECEIPT OF AND DATES FOR PHILMONT RESERVATION FOR TWO YEARS HENCE.

- REVIEW ITINERARY SELECTIONS TO ELIMINATE BLOCKED CHOICES

FEB 2000	- CREW MEETINGS

- ADVISOR MEETING: 	- PREPARATION FOR CREW & CONTINGENT SHAKEDOWNS

- SELECT ITINERARY CHOICES

- MAKE RESERVATIONS FOR “FLYING W”.

- CPR / FIRST AID ADULT TRAINING

- ORDER FOOD FROM PHILMONT FOR APRIL SHAKEDOWN HIKE

MAR 2000	- CREW MEETINGS

- SECOND SHAKEDOWN HIKE SCHEDULED TO BE HELD APRIL 7, 8, 9

- ADVISOR MEETING:	- PEAKS BOOKS RECEIVED

- ITINERARY CHOICE MEETING

- CREW SHAKEDOWN HIKES

APR 2000	- CREW MEETINGS

- ADVISOR MEETING

- ADULT ADVISOR MEDICALS DUE

- ORDER 50 MILER PATCHES FROM COUNCIL OFFICE.

- GET ZIP LOC BAGS

- GET FEEDSACKS FOR BACKPACKS

- DISTRIBUTE PETTY CASH TO EACH CREW

MAY 2000	- CONSERVATION WEEKENDS AT FORESTBURG & QUAIL HILL.  (1ST  & 2ND

CAMPBUILDERS WEEKENDS) (INCLUDES ADVISORS & CREW MEETINGS)

- CREW MEETINGS

- FINAL PAYMENT DUE TO PHILMONT

- FINALIZE ALL RESERVATIONS

- ADVISOR MEETING

- ADVISOR FEES DUE IN FULL

- VERIFY RECEIPT OF ALL PHILMONT MEDICAL FORMS AND THAT ALL ITEMS HAVE BEEN COMPLETED.

- CONTINGENT LEADER TO RETURN “ARRIVAL PLANS” CARD TO PHILMONT.

- SUBMIT NATIONAL TOUR PERMIT TO COUNCIL FOR APPROVAL..

- SUBMIT CHECK REQUESTS TO COUNCIL OFFICE  FOR PROCESSING.

- PROVIDE NAMES FOR AIRLINE TICKETS TO TRAVEL AGENT FOR TICKETING

JUN 2000	- CREW MEETINGS

- GET TAX EXEMPT FORMS

- CALL TO CONFIRM PIKES PEAK AND OTHER RESERVATIONS

- ADVISOR MEETING: DISTRIBUTE LAST MINUTE NOTES

- GET TRAVELERS CHECKS

- COORDINATE SHIPPING OF BACKPACK STOVES & FUEL CANISTERS TO PHILMONT

- CONTINGENT LEADER TO COLLECT & BRING TO PHILMONT: COPY OF COMPLETED CPR/FIRST AID

CERTIFICATION CARDS FOR ALL ADULTS, APPROVED TOUR PERMIT, CREW ROSTERS WITH ALL COPIES ATTACHED, COPIES OF PAYMENT LETTER.

JUNE  28, 2000	- PHILMONT BOUND !!!!!!

THE PRESENT PLANS FOR THE. PHILMONT 2000 TRIP REFLECT DEPARTING ON WEDNESDAY JUNE 28TH, ARRIVING AT PHILMONT ON SATURDAY, JULY 1ST, AND ARRIVING BACK HOME ON THURSDAY, JULY 13TH.

NOTE: - EACH CREW MAY OPT TO HAVE ADDITIONAL MEETINGS & HIKES

3/28/99